## Product Backlog
Epic | User Story ID | Feature/Title | User Story | Status | Acceptance Criteria
OpenCart_Epic_001 For a new e-commerce website to launch, the highest Business will be when a new user to able to buy an item from the website | US001 | Registration | As a First time visitor to the e-commerce website, I want to register my account, So that I can login to application. | New | New User should able to Register Account with Valid Data.
OpenCart_Epic_001 For a new e-commerce website to launch, the highest Business will be when a new user to able to buy an item from the website | US002 | Login | As a Registered User, I want to login to the website So that I can see my account details etc.. | New | System must validate user credentials and allow login if Credentials are correct…
OpenCart_Epic_001 For a new e-commerce website to launch, the highest Business will be when a new user to able to buy an item from the website | US003 | Logout | As a Registered User, I want to logout from website, So that no one else cannot access my account. | New | System must Logout after Login
OpenCart_Epic_001 For a new e-commerce website to launch, the highest Business will be when a new user to able to buy an item from the website | US004 | User Search Products | As a User, I want to be able to search items, So that I can add them to cart and do payment. | New | User Should able to search the products and add them to Cart

## Sprint Planning
Epic | User Story ID | Feature/Title | User Story | Story Points | Sprints
OpenCart_Epic_001 For a new e-commerce website to launch, the highest Business will be when a new user to able to buy an item from the website | US001 | Registration | As a First time visitor to the e-commerce website, I want to register my account, So that I can login to application. | 8 | 1
OpenCart_Epic_001 For a new e-commerce website to launch, the highest Business will be when a new user to able to buy an item from the website | US002 | Login | As a Registered User, I want to login to the website So that I can see my account details etc.. | 5 | 1
OpenCart_Epic_001 For a new e-commerce website to launch, the highest Business will be when a new user to able to buy an item from the website | US003 | Logout | As a Registered User, I want to logout from website, So that no one else cannot access my account. | 3 | 1
OpenCart_Epic_001 For a new e-commerce website to launch, the highest Business will be when a new user to able to buy an item from the website | US004 | User Search Products | As a User, I want to be able to search items, So that I can add them to cart and do payment. | 5 | 3
Story Points | Hours
1 | 1 Hour/1 Day(depend Upon the Company)
0,1,1,2,3,5,8 | Fibinacci Series

## Tasks
Developer Tasks | QA Tasks
Understanding Requirement | Understanding Requirements
Design | Writing Test Scenerio
Coding | Writing Test Cases
Unit Testing | Test Case Reviews
Integration Testing | Test Case Preparations
Code Review | Test Environment Setup
Bug Fixes | Test Execution
Team Meetings | Re-Testing Bugs
Any others… | Team Meetings
Automation
Any Other…